THE BHARAT SCOUTS & GUIDES

VISION 2024

PLAN FOR THE PERIOD 2014-2017

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 – 08 March 2014

| WORLD ORGANIZATION OF THE SCOUT MOVEMENT Mission Statement The mission of Scouting is to contribute to the education of young people, through a value based system based on the Scout Promise and Law to help build a better world where people are self-fulfilled as individuals and play a constructive role in society. This is achieved by: Involving them throughout their formative years in a non-formal education process Using specific methods that makes each individual the principal agent in his or her development as a self-reliant, supportive, responsible and committed person Assisting them to establish a value based upon spiritual, social and personal principles as expressed in the Promise and Law | WORLD ASSOCIATION OF GIRL GUIDES AND GIRL SCOUTS Vision: All girls and young women are valued and take action to change the world. Mission: To enable girls and young women to develop their fullest potential as responsible citizens of the world. |
| --- | --- |

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 – 08 March 2014

THE BHARAT SCOUTS AND GUIDES, INDIA

Vision Statement

By 2024, The Bharat Scouts & Guides will be a globally visible, consistently growing, self-reliant premium youth movement that is gender balanced, vibrant and responsive to trends.

Providing young people with value-based, attractive and challenging youth programme, through competent leaders, effective communication, optimum use of technology and efficient management.

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 – 08 March 2014

REVIEW SWOT ANALYSIS RESULTS

| STRENGTH | WEAKNESS | OPPORTUNITIES | THREAT |
| --- | --- | --- | --- |
| Membership growth. Availability of Trainers/Professionals. Immovable property and revenue received. Awards and Recognitions. Dedicated and committed volunteers. Literature like magazines etc. Youth Programme. Educational and value-based Movement. Govt. Support National Adventure Institute/activities. Participation and exposure in international events. Good Networking. Individual participation. (Bottom-Up method/approach) Huge literate man-power. Progressive and stimulative Badge System like Proficiency Badge. Patrol System. Organizational structure. Supply service. Support from the sister organization. Organizational network. Cultural heritage. Former scouts and guides. Financial stability | Inadequate competent trainers (in all Sections) and professionals at all levels. Insufficient supply of literature in regional languages. Limited self-generated funds and undue dependency on govt. grant Erratic communication system Lack of self-motivation Poorly developed training centres and infrastructure and poor management of existing assets. Lack of proper boundary management. Absence of visionary leadership No proper Evaluation system Poor supply service dept. Absence of Internal Customer Satisfaction models Shortage of open units and reaching out policies. No Job security Lack of upgraded and innovative Youth Programme Incentives and recog. for adult leaders Poor documentation Ambiguous RULES and Regulations. No Brand Equity Limited practice of partnership No best practices in Networking Ineffective Adult Resource Management. Improper utilization of ICT. Outdated SOT | Government aid & sponsorship High potential under CSR Latest ICT Huge youth population and scope for penetration. Bench marking with like-minded youth organisation. Existing external recognition system like Padma Awards, Duke of Eedinburg Award, Megasay, Nobel Prize, etc. | Political influences and instabilities Insurgency, Militancy, Naxalism, Terrorism, etc. Corrupt insensitive Bureaucratic practices Sprouting of unethical Parallel Organizations. Natural calamities. Information Overload. |

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 – 08 March 2014

THE BHARAT SCOUTS AND GUIDES

INDIA

Strategic Priorities:

- Youth Programme:-

To ensure that the youth programme is implemented that meets the needs of all young people.

- Adult Resources: -

This priority directs to implement National Adult Resource Policy ensuring that 	leaders in all functions are appointed.

- Management:-

To improve the overall organizational setup of the Bharat Scouts & Guides to be responsive to the changes in the internal and external environment to achieve the 	organizational goals.

- Finance: -

To improve the financial status making optimum use of existing assets and exploring new fund-generating areas stepping towards self-reliance.

- Communication and Public Relations:-

To develop an effective internal and external communication system, making use of available tools and technology enhancing visibility of Scouting/Guiding.

- Growth: -

To ensure overall annual growth by 10% by reaching out and keeping membership balance amongst the sections in both wings.

| Strategic Priority: Youth Programme To ensure that the youth programme is implemented that meets the needs of all young people. |
| --- |
| Objective - 1: To review the existing Youth Programme to meet the needs of all young people by December 2015 and implement starting December 2016. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Form a task force committee to prepare the format and guidelines in order to review the boy/girl programme section-wise by nov 2014 | An authentic format and guidelines are available to prepare the tools. | JDS |
| Start the survey by inviting the expert independent agency. They will compile the report and recommendation and submit to the task force committee by feb 2016 | Survey report received. | DDBP |
| The task force committee will then give to the review approach programme workshop after due validation by aug 2016 | The task force committee will understand the survey. | JDS |
| The review approach programme committee consist of expertise will design the activities, method and purpose will be submitted to the rules committee with the recommendation of the revised youth programme by sept 2016. | The rap has prepared the revised youth programme | JDS |

| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| --- | --- | --- |
| The same recommendation will be put up to the national executive committee by sep 2016 for approval. | Received approved recommendations available. | JDS |
| The final recommendation of revised boy/girl programme will be put up to the national council for approval by nov 2016. | Received approved recommendations available. | JDS |
| The revised youth programme will be circulated electronically to the state association with immediate effect for implementation by dec 2016 | Attractive and challenging programme will be revised, circulated and implemented. | DIRECTOR |

| Strategic Priority: Youth Programme To ensure that the youth programme is implemented that meets the needs of all young people. |
| --- |
| Objective - 2: to continue to provide exposure to young people through youth programme activities at all levels starting april 2014 | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Circulate the scheduled annual programme activities by April annually. | Advanced information available to all state | Director |
| Conduct annually: National integration Camps, Rovers/Rangers Samagam Cubs & bulbuls Utsav Service camps | Exposure to young people to different cultures, Developed spirit of brotherhood Developed confidence | JDS |
| National jamborees in 2014. |  | JSD |
| Ensure active participation by maximum states |  | JDS |

| Strategic Priority: Youth Programme To ensure that the youth programme is implemented that meets the needs of all young people. |
| --- |
| Objective – 3: To develop partnership with other organizations to provide opportunities for exchange of programme activities by starting Nov, 2014 | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| The scout/guide sub-committee to identify other organizations to partner with, to provide opportunities to young people in participating in developmental activates not available within scouting by Aug annually | List of organizations available of potential partners | JDS/JDG,SOCs |
| To decide the areas/activity of partnership and other related terms and conditions by September annually | Necessary basic data available for partnership | JDS/JDG, SOCs |
| Enter into partnership agreement with the agencies | Partnership conditions mutually agreed | JSD/JDG, SOCs |
| Selection of participants |  | JDS/JDG, SOCs |
| Implementation/participation in partnership project |  | JDS/JDG, SOCs |
| Regular monitoring of project implementation/ participation |  | JDS/JDG, SOCs |
| Prepare post project/participation report and submit to appropriate authorities |  | JDS/JDG, SOCs |

| Strategic Priority: Adult Resources This priority directs to implement National Adult Resource Policy ensuring that leaders in all functions are appointed. |
| --- |
| Objective-1: To implement the revised NARP starting December’2014 | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Develop a format at National level for feedback of present status of NARP at all levels by May’2014 | A format of feedback, sent to states for feedback | JD S |
| Submission of information of NARP on prescribed format online/email from states by June’2014 | Submission of format from the states | STC(S/G), JD S |
| Analyze the information received from the state and prepare a report and submit to NARP Committee by July’2014. | Report of information received are prepared | JD S |
| NARP Committee to analyzes report, revises the policy and submit recommendation to rules committee by Aug’2014 | Recommendation for implementation of revised NARP prepared | Jt DIR(S) |
| Submission of recommendation duly approved by Rules committee to National Executive Committee/National Council by Nov ’2014 | Approval of the National Council and National Executive with any amendments. | Jt. Dir (SS) |
| Develop tools, organize workshop seminars, |  |  |
| Implementation of the revised NARP by the states starting from April 2015 | Revised NARP circulated to all the states for implementation | STC(S/G)/ SARP/DARP |
| Monitor support |  |  |
| Review of implementation of revised NARP at all levels by July’2015 | To Get feedback from the states for its implementation and further ensure its implementation for defaulters | Jt. Dir(SS), DDSLT, DDGLT STC(S/G)/SARP/DARP |

| Strategic Priority: Adult Resources This priority directs to implement National Adult Resource Policy ensuring that leaders in all functions are appointed. |
| --- |
| Objective-2: To revised and implement the SOT in line with NARP BY DEC 2016 | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| NHQ to invite proposals for changes required n in the SOT from Training Team members by April2014formulate the communication policy by June 2014 | Proposals are being received and consolidating at NHQ. | JD(S)/JD (G) |
| Organise SANDHAN BY MAY 2014 recommend changes for approval of National Executive Committee and National council. | Draft of revised SOT will be ready for submission | JD(S)/JD (G) |
| Adoption of revised SOT by Sept. 2014 | Revised SOT Will be ready after getting approval of NC. | JD(S)/JD (G) |
| Circulate the changes adopted to all states by December 2014 |  | JD(SS) |
| Disseminate the Revised amendments in the State level Executive Meet in March 2015 and they will ensure it’s implementation by Dec. 2016 | All the State level Executives will be aware of changes and later on will report to NHQ about its implementation | JD (S) /STC (S) |

| Strategic Priority: Adult Resources This priority directs to implement National Adult Resource Policy ensuring that leaders in all functions are appointed. |
| --- |
| Objective-3: To ensure by 2016 competent leaders at all levels are trained and appointed in the areas that they are responsible. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Prepare Training Handbooks/Training Handouts as per the syllabus in the revised SOT all positions/trainers by March 2015, by taking assistants of the experts within and outside the Organisation. | The revised Training Handbooks and materials will be ready. | JD (S)/JD (G) |
| All LTs, STCs will be trained at NTC on the revised Course Plan by June 2016 | All key persons will be trained | JD (S)/JD (G) |
| The State with the help of NTC will organise further training Courses to train their other functionaries by Dec. 2016 | The adult Leaders/Trainers will be develop competency in their respective areas. | JD (S)/JD(G) & STC(S)/STC(G) |

| Strategic Priority: Management To improve the overall organizational setup of the Bharat Scouts & Guides to be responsive to the changes in the internal and external environment to achieve the organizational goals. |
| --- |
| Objective - 1: By December 2015, review the existing staff regulation to include personal development, support, recognition, incentive and empowerment of Scout/Guide professional at National and State level to ensure they are motivated and competent in their functional areas. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) | Resources Required |
| Form a committee to review and revise staff service conduct rule by June-2014. | Formation of Committee | DIRECTOR/SS | Existing Service & conduct rules |
| Review the existing revise staff service conduct rule and create a friendly atmosphere and give recognition and incentive to the staff by July-2014. | Draw backs identified of the existing staff service conduct rule. And good working environment. | DIRECTOR/SS |  |
| Discussion on the new service rule book and delegation of the work in the office at all level by August-2014. | Amendment of rules. Performance in work. Keeping in view of one post for one person. | DIRECTOR/SS |  |
| Final recommendation to higher authority and updating training of professionals in their concern departments by September-2014. | New service Rule. Improving competency in their area. | DIRECTOR/SS | Experts |
| Approval by competent authority October-2014 | Publication of new staff conduct service Rule. | DIRECTOR/SS |  |

| Strategic Priority: Management To improve the overall organizational setup of the Bharat Scouts & Guides to be responsive to the changes in the internal and external environment to achieve the organizational goals. |
| --- |
| Objective - 2: By December 2016 review the existing policy and system and strengthen the overall set- up of BS&G including infrastructure. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Form a committee to updating the rules by January 2015 | Committee formation | DIRECTOR/SS |
| Review of existing rule and discussion about the insurance system by March 2015 | Knowledge about the existing rule. | DIRECTOR/SS |
| Approval by the competent authority by May 2015 for insurance system. |  | DIRECTOR/SS |
| Implementation of the insurance system by October 2015 | Feeling of security | DIRECTOR/SS |
| Renovation of office buildings by November 2015 | Modern facilities | DIRECTOR/SS |

| Strategic Priority: Finance To improve the financial status making optimum use of existing assets and exploring new fund-generating areas stepping towards self-reliance. |
| --- |
| Objective - 1: Ensure generating the funds & its proper utilization at all levels by December 2017. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) Resources Required |
| Develop Financial Rules and procedures to be followed by States and circulate it by September 2014. | All States have minimum financial standards guide to follow. | JDSS |
| Develop Fund raising and Partnership Guideline for all level for generating funds by December 2014. | Standard guideline available at all level for fund rising and partnership. | JDSS |
| Annually collect the Financial Report from the States and give feedback as needed to States starting April 2015 | Improved financial management at all level. | JDSS |
| Monitor the progress twice a year and extend support to States where necessary Starting December 2014 | Continues strengthening of financial management at national and Sub National Level | JDSS |

| Strategic Priority: Finance To improve the financial status making optimum use of existing assets and exploring new fund-generating areas stepping towards self-reliance. |
| --- |
| Objective - 2: To ensure annual increase of 5% income at all levels through various sources such as Supply Service, Flag Day, Magazine Subscription by the end of March 2015. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Supply Service department to be strengthen by providing qualitative and adequate Scout/Guide material and literature by October 2014 | Sufficient material will be available to fulfill the requirement of the States. | SSO |
| Promote attractive gift items & souvenirs by October 2015. | Materials are procured and supplied as per demand | SSO |
| Ensure Magazine Subscription increased by motivating members at Grass root level by March 2015 | Increase in revenue and visibility. | PRO/SS/DS |
| Promote Importance of BSG to the public by Sale of Flag Day stickers annually. | Funds available to support raising of infrastructure & to support unprivileged young members for participating in overseas events. | JD (SS)/SS |

| Strategic Priority: Finance To improve the financial status making optimum use of existing assets and exploring new fund-generating areas stepping towards self-reliance. |
| --- |
| Objective - 3: Promote relationship with corporate sector/other agencies for sponsorship/ partnership programme and implement at least one Project at all level by the end of May 2015 | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Develop a external Public Relation policy by Nov, 2014. | Public Relation policy developed | JDSS |
| Finalise and run at least one project at National, State & District. | Present status of project will be known | JDSS |
| Objective - 4: Ensure increasing of at least 10% revenue at all levels through rental of buildings, training Centre and other assets by the end of March 2016. |
| Collect information of the present assets and position of BSG at all level by March 2015 | National/ State/ Dist. Association will have complete records on assets. | JDSS/SS |
| Analysis of information, Highlighting assets and liabilities with the recommendation on how to generate income from the assets by December 2015. | Information available for future planning. | JDSS |
| Ensure each Dist. has their own supply service with at least basic need of Scouts and Guides by March 2016. | Scouts / Guides equipment made available | JDSS/SS/DS |

| Strategic Priority: Finance To improve the financial status making optimum use of existing assets and exploring new fund-generating areas stepping towards self-reliance. |
| --- |
| Objective - 5: Develop at least one Revenue earning Centre by March 2017. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Meetings of development and finance committees conducted to identify & finalise the project by Dec,2014 | Project details will finalised. | DIRECTOR/SS/DS |
| Develop vocational training centre such as Tailoring, Handicraft, Vocational crafts etc which can be feasible by April 2015. | Members as well as local people are trained in various skills. | JDSS |
| Ensure sale of materials prepared by the members. | Wide publicity & revenue. |  |
| Objective - 6: Recruit at least 1 member per State for Bharat Scouts and Guides Foundation annually starting from April 2014. |
| To prepare appeal highlighting various Schemes of BSG Foundation April, 2014. | Appeal made available at all level through circular and brochures. | DIRECTOR |
| State to recruit at least 1 foundation member annually. | At least 40 members are recruited annually | SS |

| Strategic Priority: Communication and Public Relations To develop an effective internal and external communication system, making use of available tools and technology enhancing visibility of Scouting/Guiding. |
| --- |
| Objective - 1: To implement the communication policy through the optimum use of Information Technology starting by December 2014 | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| To constitute an expert committee at NHQ to formulate the communication policy by June 2014 | A proposed documented policy will be available | JDSS |
| To adopt the policy by the National Council by November 2014 | A communication Policy is available for implementation. | JDSS |
| Disseminate policy documents of the policy to all the states by December 2014 | States will enforce the policy | JDSS |
| Objective - 2: To create a Brand Strategy including protection of BSG intellectual property and disseminate to all states for implementation By March 2015. |
| Using the support from concept branding experts, develop a brand manual by sep. 2014 | A proposed brand manual is available. | JDSS |
| Adopt the brand manual in the National Council by Nov. 2014 | Approved brand manual is ready for adoption by States | JDSS |
| Disseminate the brand manual to all States for implementation by Jan 2015 | The States will implement the brand manual | JDSS |
| Register the Intellectual Property (Emblem, literature etc.) by Dec 2015 | Intellectual property of BS&G are secured | JDSS |

| Strategic Priority: Communication and Public Relations To develop an effective internal and external communication system, making use of available tools and technology enhancing visibility of Scouting/Guiding. |
| --- |
| Objective-3: To Formulate and implement Marketing Strategy for promoting Scouting/Guiding starting by December 2017. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Using the support from experts, formulate a marketing strategy for promoting Scouting and Guiding by March 2015 | Marketing strategy is prepared | DIRECTOR |
| The implementation of the strategy as a pilot project by NHQ to be under taken in one State of each region by March 2016 | Pilot project is implemented and results are evaluated | DIRECTOR/ ASST. DIRECTOR |
| Revise the strategy based on the feedback from pilot project by Sep 2016 | Revised strategy is implemented | DIRECTOR |

| Strategic Priority: Growth To ensure overall annual growth by 10% by reaching out and keeping membership balance amongst the sections in both wings. |
| --- |
| Objective - 1: To ensure overall membership growth by 10% in each sections and at least 2% reaching out starting by 30th June 2014. | Expected Results: |
| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| Analise the Membership data required from State for in 2012-2013 by April 2014 | Required data is available at NHQ for further action. | JDSS/State Secretary |
| Based on analysis set target for each State clearly starting to expected members increase in each State based on the scope and communicate to the responsible State accordingly by May 2014. | State wise information for proceeding with the process is available. | JDSS/State Secretary |
| Minimum quarterly (end of the month) with state on the progress and support needed. | Job completed every quarter is available at NHQ for evaluation and further action. | JDSS/State Secretary |
| Extend support as required State for achieving the target. | Information of the requirement of the State is available at NHQ for necessary support. | JDSS/State Secretary |
| Collect from APR and other NSO’s implement registration system by June 2014 | System of registration from APR and NSO’s is available for follow up action. | JDSS/State Secretary |
| Review the progress annually and set target accordingly starting by September 2014. | Requirement of evaluation up to date is available. Further guidance can be given on the basis of evaluation. | JDSS/State Secretary |

| Action Steps | Expected Outcome/ Results | Who (Key Person) |
| --- | --- | --- |
| Review and update the existing members of administration system by December 2014. | Up dated list of the members of administration is available for job allotments. | JDSS/State Secretary |
| Develop necessary procedure and tools by March 2015 and dispatch to state for its implementation. | Procedure and tools developed is available at States for implementation and further action. | JDSS/State Secretary |
| If required find sponsor to fund the development of data base by March 2015. | Sponsorers are available for funding for the development of data base system. | JDSS/State Secretary |
| Contact appropriate vender for developing data base programme by September 2015. | Vender for developing the data base programme is available. | JDSS/State Secretary |
| Development and testing of data base by December 2015. | Developed data base system is tested and ready for put to use. | JDSS/State Secretary |
| Training of State Leaders as using data base programme by March 2016 | Trained leaders of States in using the data base programme are available at the State. | JDSS/State Secretary |
| Implementation by July 2016 | Data base programme is implemented. | JDSS/State Secretary |
| Monitoring, Evaluation of new System by October 2016. | Data base new system after monitoring and evaluation is readily available for further use. | JDSS/State Secretary |

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 to 08 March 2014

EVALUATION CRITERIA

| When | What | How | Who |
| --- | --- | --- | --- |
| National Level December 2015 June-2016 Nov-2017 Repeated Annually | Action V/s Outcome Objectives V/s Achievements Achievements V/s Vision | Interactions , Survey, Meeting individual Reports | NEC Strategic Plan Implementation Task Group |
| State Level Aug.-2015 May-2016 August-2017 End of each phase | Action V/s Outcome Objectives V/s Achievements Achievements V/s Vision | Interactions , Survey Meeting individual Reports | SEC SS SOC/STC |

SUPPORT INFRASTRUCTURE

|  | Suggested Infrastructure (Committee/ Task Group/ Individual | Remarks |
| --- | --- | --- |
| 1. Overall Monitoring of plan implementation | Strategic plan Implementation Task Group | NHQ Executive not below the Rank of Jt. Director |
| 2. Monitoring Plan by Priority Area • Youth Programme | Scout Sub-Committee Guide Sub-Committee | JD(S/G) & SOCs |
| • Growth | Scout Sub-Committee Guide Sub-Committee | JD(S/G) & SOCs |
| • Finance | Finance Committee | JDSS/SS |
| • Adult Resources | Adult Resources Management Committee | DDSLT & DDGLT STCs |
| • Management | National Executive Committee State Executive Committee | Director/ SS |
| •Communications And Public Relations | Public Relation Committee | JDSS/ SS |

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 to 08 March 2014

Recommendations

The Recommendation Committee of the National Strategic Planning Workshop, 2014 has the pleasure in recommending the following salient points for the kind perusal and necessary action by the Hon’ble National Commissioner for the effective implementation of the Strategic Plan – Vision 2024.

- To accept the Strategic Plan as presented for better performance of the Bharat Scouts & Guides as the premier Youth Movement in the Country.

- To constitute a “Strategic Plan Implementation Task Group under the chairmanship of the National Commissioner to ensure the successful implementation of the Strategic Plan. List of suggested members annexed in second page.

- Identify a Core Group of internal resource persons from among the workshop participants to conduct/assist similar workshops at the state level.

- To appoint a Nodal Officer not below the Rank of Jt. Director with specific Terms of Reference, to monitor the implementation of the Strategic Plan at the National Headquarters and similarly at the state level not below the rank of SOC/STC.

- Necessary Budgetary provisions to be made to meet the expenses incurred in achieving the objectives of the Strategic Plan.

- To depute a delegation along with the NHQ Commissioner of the specific Region to support the States in implementing the Strategic Plan.

- The progress of the Strategic Plan is to be included as an agenda in all meetings of respective Sub-Committees, Planning Committee Executive Committee, Council, and to be presented along with a Summary Strategic Report at national and state level.

- All future programmes/events to be planned in line with the Strategic Plan.

- NHQ/Staff should be updated with logistic and infrastructural support to facilitate the implementation of the Strategic Plan.

- A Youth Programme Development Workshop and a AIS Workshop for the SCC/SC/SS/SOCs/STCs is to be conducted with support from WOSM/WAGGGS.

- A Check and Balance approach be adopted in all Committees framed in our Organisational structure including the Finance Committee to allow accountability and transparency.

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 to 08 March 2014

Recommendation Committee-

- Mr. B. Ramesh Patnaik, State Secretary/ CG Chairman

- Ms Indrani Rao, SOC(Southern Railway) Secretary

- Mr. C.S. Reddy, STC(S), Karnataka

- Mr. Arvind Shrivastava, STC(S), Uttar Pradesh

- Ms. Chanyan Lowang, SOC(G), Arunachal Pradesh

- Mr. Gary James, SOC(S), Meghalaya

- Ms. Suyesh Lodha,DOC(G), Rajashthan

- Mr. K. Sukumara, Dy. Director(AP), NAI and Coordinator

i) Chairman 			– National Commissioner

ii) Vice Chairman

iii) Members -	 		Chairman – Scout Sub Committee

iv) 				Chairman – Guide Sub Committee

v) 				Chairman – Finance Committee

vi)				Chairman – Rules Committee

vii) 				Chairman – NARP

viii) 				Chairman – PR

ix)  4 participants from the Strategic Planning Workshop (2 Scout Wing and 2 Guide Wing)

x)    Secretary – 		Nodal Officer

National Strategic Planning Workshop

Bharat Scouts and Guides

National Headquarters ( New Delhi, India

04 to 08 March 2014

Responsibilities of Members-

- National Commissioner :-

Ensure the programme of plan in National Executive Committee, collect the reports of each of the member before presenting it in National Executive Committee.

- Vice Chairman :-

Preside the Committee Meetings  in absence of  the National Commissioner  and assist National Commissioner in all his responsibilities.

- Chairman – Scout Sub Committee: -

Will be in change of implementation of Boy Programme and submit report to the National Commissioner.

- Chairman – Guide Sub Committee:-

Will be in- charge of implementation of Girl Programme and submit report to the National Commissioner.

- Chairman - Finance Committee: -

Will look after the growth of Finance of BS&G to submit report to the National Commissioner

with the assistance of National Treasurer.

- Chairman -Rules Committee:-

Will look after the Membership Growth and Management of Bharat Scouts & Guides and submit

the  report to the National Commissioner.

- Chairman- NARP:-

Will look after the implantation of NARP and submit report to the National Commissioner.

- Chairman Public Relation Committee: -

Will look after the communication and public relation of Bharat Scouts & Guides and submit report to the National Commissioner.

- Secretary :-

Will assist the National Commissioner in documentation, secretarial work, convene the meeting and coordinate in all the works of members and apprise the National Commissioner from time to time.